## Sheet1
Sprint 1 Backlog
Sprint Number | 1 | Start Date | 2015-06-22 | End Date | 2015-06-26
Product Backlog ID | User Story | Done Definition | Tasks | Task ID | Estimate (hrs)
PoolOne.0001 | Adverse Drug Event Reports Since 2004
|  |  | Requirements | 1.001 | 5
|  |  | Create UI with Angular JS MVC Pattern | 1.002 | 5
|  |  | Create Angular JS Service to consume Open FDA REST Resource | 1.003 | 2
|  |  | Investigate Response Object and create graph | 1.004 | 2
|  |  | Create D3 Service to display data in a graph. | 1.005 | 6
|  |  | Perform Unit Testing | 1.006 | 4
|  |  | Perform functionality and 508 compliance testing using FireEye and documented the results | 1.007 | 6
Total for Adverse Events Due to Drugs |  |  |  |  | 30